## Instructions
Requirements Manager: | Instructions
Project: | [ Project Name ] | Project ID: | [ Prj Unique ID ] | As Of: | [ Date of Doc Update ]
Project Manager: | [ PM Name ]
Enter values in this Instruction tab's header for Project Name, PM Name, etc. The entered values will be reflected in the subsequent tabs.
Key Stakeholders
Analysts | Use the Req Tree tab to capture requirements as they are elicited and defined.
Developers | use the Req Tree tab to guide design and the decomposition of functional requirements to technical requirements. The RTM helps assure two things for the Development Team: 1) all business / functional requirements are met in the solution, and 2) no work is planned that does not address one or more requirements.
Testers | The Test team can commence test planning and test case development upon approval of requirements. They can use the RTM to assure complete and appropriate coverage.
PM | The PM should be concerned on Day One with how the project will be accepted and successfully closed. The requirements, if properly completed and with signed-off fit criterion give an objective measure with certainty as to acceptance when met. The RTM provides assurance each are being met in the design, addressed in testing, and as test results are recorded , completion of the work at a level the customer is obligated to accept. This document, with requirements approval, provides an important baseline from which change in scope can be detected and measured, then addressed.
Clients | As the project's design matures and moves into construction, then test, the client can be assured via the RTM as to how their requirements are being met.
Req Tree | Description | Range of Values
Approver | Who will have standing and authority to approve the requirement.
Apprvl Date | Date of approval
Assumption | If there are material assumptions, document them in this work book and reference the Assumption ID here.
Fit Criterion | Objective and quantifiable measure of the solution's attainment of the requirement. This will be the criterion the subsequent testing will use. If a fit criterion can not be adequately defined, the requirement is unclear, incomplete, or otherwise unattainable and unenforceable. Change it, for there is no way of knowing when it has been satisfied.
Reference | Specify Use Case ID, Screen Shot, diagram, or what have you here.
Req Description | A terse statement of the requirement. Each requirement should be verifiable, necessary, attainable, and clear. It should express what is needed, not how it is to be done.
Req ID | Unique ID, preferably in a hierarchical structure that can evolve and expand as the requirements set matures. 1.1.3.5 as an example. Like a WBS, portions of the tree should relate to like or related requirements. Thus 1.1.3.5 and 1.1.3.7 are relating to a logically common portion of the requirements (e.g. 1.1.3 - Login Process). | x.x.x.x etc
Req Type | Functional Requirements are statements of required functionality or behavior that the product will exhibit under specific conditions. These are “what the product must do” from the perspective of the client. Non-Functional Requirements include the characteristics the product is expected to exhibit beyond the functional behavior. Examples include requirements for system performance, configuration, usability, portability, maintainability, safety, security, or to meet legal requirements. Non-Functional requirements are along the lines of “how the product must do what it does.” Constraints are mandates that may limit or even specify design decisions and solutions. Examples often include requirements for interfaces to legacy systems, or use of specific protocols to satisfy their needs. | Functional Non-Functional Constraint
Source | Who identified the requirement - Mostly this will be someone on the client side, but specifically who, and what role or standing? Whom would you ask subsequently if there are questions or issues effecting the requirements? Valid citations here might be the contractual docs governing the project. Examples: Statement of Work 3.4.7, System Spec 4.2, Contract 7.2a Other key sources of requirements include technical docs such as Product Specifications, Hardware Specifications, standards body RFPs and the like.
Status | Last significant milestone achieved for the requirement, or current progress against the next milestone.
Ver Method | How will the Fit Criterion be measured and verified? Common means include any combination of Analysis, Test, Inspection, or Demonstration. | Analysis Test Inspection Demonstration
Ver Type | What method will be used to establish evidence of the requirement's completion? | Unit Test SIT Inspection Demonstration UAT Regression
Req Traceability Matrix
The Bi-Directional Requirements Traceability Matrix provides an efficient and effective method for tracking requirements through the project development life cycle from the point of requirements definition to the point of implementation. It is especially useful in identifying the impacts of change requests, as well as in incorporating such changes into design, development, and testing. Development of this matrix is required only for large projects, however it is recommended for ALL projects.
Assumptions
Assumption | Brief but clear and complete statement of assumption.
Assumption ID | Unique ID, serial is fine.
Date | Date of discovery / entry
Entered by | Who wrote it up
Source | Where did this assumption originate or became material?
Status | What is current state or status of the assumption | Proposed Valid Satisfied Inactive

## Req Tree
Requirements Manager: |  |  | Requirements Tree
Project: |  |  | [ Project Name ] | Project ID: | [ Prj Unique ID ] | As Of: | [ Date of Doc Update ]
Stakeholders:
Client:
|  | PM: | [ PM Name ]
Analyst(s):
| Req ID | Req Type | Req Description | Reference | Assumption | Source | Fit Criterion | Ver Method | Ver Type | Approver | Apprvl Date | Status
| BR-1 | Functional | Product shall provide users with secure, private WWW sessions. |  | 1, 2 | Product Concept Doc | Addressed in related FR and DR items | Analysis | Demonstration | Betty Boop | 2007-07-11 | Approved
| BR-2 | Constraint | Product user validation shall implement LDAP to comply with existing Single Sign-On environment | Arch Diagram v2.3, dated 23 Aug, 2007 | 3 | Services Contract 2701 dated 4 Jun 2007 | Correct communication and implementation of data transfer with legacy LDAP server. | Demonstration, Test | SIT | Betty Boop | 2007-07-11 | Approved
| FR-1 | Functional | Secure log in screen via https shall provide access control for the service |  | 1, 4 | BR-1 | Login function shall allow all authorized users to execute the service, and prevent any unuathorized user from accessing the service. | Test | SIT | Betty Boop
| FR-2 | Functional | User password entry area on login screen shall obscure the text entry display so that the password value will not be viewed. |  |  | BR-1 | Password entry display does not show readable value when password is entered. | Demonstration, Test | SIT, UAT | Betty Boop
FR-3

## RTM
REQUIREMENTS TRACEABILITY MATRIX
PROJECT NAME: |  | [ Project Name ]
PROJECT ID: |  | [ Prj Unique ID ]
PROJECT MANAGER: |  | [ PM Name ]
BUSINESS ANALYST:
REQUIREMENTS ANALYSIS PHASE |  | DESIGN PHASE | [5 empty] | CONSTRUCTION PHASE |  | TEST PHASE |  | RELEASE Planning |  | IMPLEMENTATION
BUSINESS REQ NO. | BUSINESS REQUIREMENT NAME/DESCRIPTION | FUNCTIONAL REQ NO. | FUNCTIONAL REQUIREMENT |  | TECH DESIGN REQ NO. | DESIGN COMPONENT |  | CONSTRUCTION COMPONENT |  | TEST CASE |  |  |  | CONSTRUCTION COMPONENT
|  |  | Name/Description | Verified By Initials |  | Component Name | Verified By Initials | Component Name | Verified By Initials | Test Case No. | Verified By Initials | Release Index | Released | Component Implemented? | Verified By Initials
BR-1 | Product shall provide users with secure, private WWW sessions. | FR-1 | Secure log in screen via https shall provide access control for the service |  | DD | [6 empty] | 1
BR-1 |  | FR-2 | User password entry area on login screen shall obscure the text entry display so that the password value will not be viewed. |  | DD | [6 empty] | 1
BR-2 | Product user validation shall implement LDAP to comply with existing Single Sign-On environment | FR |  |  | DD | [6 empty] | 1
BR |  | FR |  |  | DD | [6 empty] | not assigned
BR |  | FR |  |  | DD | [6 empty] | not assigned
BR |  | FR |  |  | DD | [6 empty] | not assigned
BR |  | FR |  |  | DD | [6 empty] | not assigned

## Assumptions
Requirements Manager: |  | Assumptions
| Project: | [ Project Name ] | Project ID: | [ Prj Unique ID ]
Assumption ID | Assumption | Entered by | Date | Source | Status | Comment
1 | Industry standard SSL protection of HTTP communications between the HTTPS server and SSL capable browser will be sufficient for establishing security of the session | Bill Door | 2007-07-10 | Product Concept Document | Satisfied | Per eMail with Betty Boop 7/12/2007 10:15
2 | Cookies and database-managed session attributes will be sufficient to provide personalized session continuity | Connie Terry | 2007-07-11 | Product Concept Document | Satisfied | Telephone discussion with Betty 7/11/2007 at 2 PM
3 | Relevant users are established in the LDAP server database, correctly and in accordance with LDAP standards. | Bill Door | 2007-07-11 | Services Contract 2701 dated 4 Jun 2007 | Proposed
4 | Authorized Users = those properly configured in LDAP (customer responsibility) | Bill Door | 2007-07-11 | FR-1 | Proposed

## Requirements Baseline
Requirements Manager: |  | Requirements Baseline
| Project: | [ Project Name ] | Project ID: | [ Prj Unique ID ]
Release ID | Release Title | Release Date | Req Comp | Code Comp | Test Comp | UA Sign-Off
1 | Phase I - Initial Capability | 2007-12-14 | 2007-08-30 | 2007-10-31 | 2007-12-07 | 2007-12-09
2 | Phase II - MyCoolNewFeature | 2008-02-15 | 2007-10-31 | 2007-12-21 | 2008-02-06 | 2008-02-08
3
4
Req ID | Requirement | Release ID
BR-1 | Product shall provide users with secure, private WWW sessions. | 1
BR-2 | Product user validation shall implement LDAP to comply with existing Single Sign-On environment | 1
FR-1 | Secure log in screen via https shall provide access control for the service | 1
FR-2 | User password entry area on login screen shall obscure the text entry display so that the password value will not be viewed. | 1
FR-3 | Some aspect of MyCoolNewFeature | 2