## Slide 1: Development of Highrise ERP system for managing and tracking the procurement
Prepared by
Ashay Pillewan
Date 5th Jan 24

## Slide 2: Project Initiation
The project was initiated to address the inefficiencies and inaccuracies of the current manual marks entry system. By creating a secure, user-friendly portal.
The project aims to streamline the supply chain process, reduce errors, and provide remote access, reduce timelines to procure the objectives and manage the workflow for the approval.
This will also enable to manage the confidential documents and for forming the centralized sourcing system with effective rates.

## Slide 3: Situation
Currently the procurement procedures are manual and time consuming. The user is not able to track the procurement status and approval required. Currently it takes 7 to 8 days for release a purchase order in the manual system.
Enormous physical documents are required to process the procurement.
Current system is person specific rather that system oriented.
Centralized tracking and MIS updates are cumbersome to generate, and analysis is not possible for generating the management insights for value additional and enhance the effectiveness.

## Slide 4: Current Problem
Generating the timely reports is a challenge.
Globalized rates are not getting tracked for the rate contract.
Tracking the approvals and delays are hectic.
Process is not automated and system document depository is not available
Workflow is not mapped, and clear roles and responsibilities are not defined.
The manual process is time consuming, and it takes 7-8 days to release the order to the vendor partner.
The system is not agile to accommodate any change request, and it doesn't not cater to the urgency of the business in critical situation.

## Slide 5: Opportunity
Streamline Procurement: Automate and optimize the entire process.
Reduce PO Generation Time: Significantly cut down on time to create purchase orders.
Efficient Role Mapping: Clearly define and assign responsibilities.
Eliminate Manual Processes: Replace manual workflows with digital automation.
Increase Accuracy: Ensure precise order generation and reduce errors.
Global Rate Mapping: Access cost-effective, global procurement rates.
Cloud-Based Data Storage: Store data securely for long-term analysis.
Faster MIS Reporting: Generate detailed reports in hours, not days.

## Slide 6: Goals / Purpose statement
Streamline and automate the procurement process.
Reduce the time required to generate purchase orders (POs).
Clearly map roles and responsibilities for efficient workflow management.
Eliminate manual processes and replace them with digital automation.
Enhance accuracy in order generation, minimizing errors.
Access global cost-effective procurement rates.
Securely store data in the cloud for long-term analysis.
Enable faster MIS reporting, reducing reporting time from days to hours.
Improve overall procurement efficiency and support data-driven decision-making.

## Slide 7: Project Objectives
Solution Selection Based on Design Criteria, Specifications, and Requirements: Identify and select the Highrise ERP solution that meets all business requirements, design specifications, and technical standards for procurement automation.
Solution Prototyping and Testing: Develop prototypes of the Highrise ERP system, followed by thorough testing to ensure functionality, performance, and alignment with user requirements.
System Design and Architecture: Define the technical architecture and design of the ERP system, ensuring scalability, security, and integration with existing infrastructure.
Custom Development and Feature Implementation: Customize and develop specific features of the ERP system, including automated workflows, role management, and data validation, according to business needs.
Data Integration and Migration: Implement seamless data integration from legacy systems into the Highrise ERP, ensuring accurate and consistent data migration.

## Slide 8: Project Objectives
User Interface (UI) and User Experience (UX) Design: Design an intuitive and user-friendly interface to ensure smooth adoption and usability for all stakeholders.
System Security and Compliance: Develop and integrate security protocols to safeguard sensitive procurement data and ensure compliance with relevant data protection regulations.
Performance Optimization and Load Testing: Ensure the system performs optimally under high loads and large datasets through extensive performance and load testing.
Cloud Infrastructure and Data Storage: Develop cloud infrastructure to enable secure, scalable storage of procurement data and facilitate real-time reporting and analytics.

## Slide 9: Project Objectives
Reporting and Analytics Development: Implement reporting and analytics features that allow real-time data visualization, faster MIS reporting, and informed decision-making.
User Training and Documentation: Develop user training programs and comprehensive documentation to support seamless onboarding and effective system use.
Post-Implementation Support and Maintenance: Set up ongoing support and maintenance plans to address issues, updates, and enhancements after system deployment.

## Slide 10: Success Criteria
Procurement Workflow Automation: Automate 90%+ of manual tasks (order creation, approvals, tracking).
PO Generation Time Reduction: Cut PO creation time by 50%, from 7 days to 3-4 days.
Role-Based Access: Implement 100% role-based access with clear responsibility mapping.
Process Digitization: Eliminate 95% of paper-based workflows and reduce errors.
Order Accuracy: Achieve 99%+ order generation accuracy.
Global Rate Integration: Leverage global procurement rates for 80%+ of decisions.
Cloud Data Storage: Store 100% of procurement data securely in the cloud.

## Slide 11: Success Criteria
Faster MIS Reporting: Generate reports in under 4 hours (70% reduction in time).
System Scalability: Handle 100% increase in procurement volume without performance loss.
System Reliability: Achieve 99.9% system uptime with support for 500+ concurrent users.
Security & Compliance: Full regulatory compliance and zero security breaches.
User Adoption: Achieve 95% adoption within 3 months, with 85%+ satisfaction.
Training Completion: 100% training completion with 85%+ pass rate.
Issue Resolution: Resolve 95% of critical issues within 24 hours, 90% of others within 48 hours.
ROI: Achieve positive ROI within 36 months through reduced cycle times and costs

## Slide 12: Methods / Approaches
1. Project Initiation
Define objectives, scope, and stakeholders
Conduct needs assessment and review current processes
2. Elicitation Techniques
Interviews: Gather insights from stakeholders
Surveys: Collect quantitative data
Workshops: Brainstorm solutions and prioritize features
Observation & Prototyping: Understand workflows and refine requirements
3. Stakeholder Analysis (RACI/ILS)
Define roles & responsibilities (RACI Matrix)
Manage expectations and communication

## Slide 13: Methods / Approaches
4. Key Documents
BRD, FRS, Use Cases, Test Plan
UAT Plan, Training Materials
5. Document Sign-off
Share drafts, gather feedback, and obtain approvals
6. Client Approvals
Present documents, clarify details, and secure formal sign-off
7. Communication Channels
Regular meetings, emails, and project tools

## Slide 14: Methods / Approaches
8. Change Request Handling
Capture, assess, and approve changes through a formal process
9. Progress Reporting
Share status updates and highlight key achievements
10. UAT & Client Acceptance
Coordinate UAT, provide support, and obtain final sign-off

## Slide 15: Resources
People – Project Team Members
Client Community:
  Procurement Team: Key stakeholders responsible for defining business requirements.
  Finance Team: Provides input on budget management and cost control.
  IT Team: Supports system integration, technical setup, and ongoing maintenance.
  End-Users: 500 employees across various departments who will be trained and onboarded.

## Slide 16: Resources
ITS Team:
  Business Analysts: Lead requirement gathering and ensure alignment with business goals.
  Developers: Responsible for customizing the ERP solution and ensuring integration with existing systems.
  UI/UX Designers: Design user-friendly interfaces.
  Testers: Conduct thorough testing of the system to ensure it meets business requirements.
  Trainers: Develop training materials and conduct training for end-users.
Estimated Cost for People:
Client Community (Internal Teams): Rs. 1,500,000
ITS Team (External Consultants & Internal Resources): Rs. 4,000,000

## Slide 17: Resources
Time – Implementation Duration
Timeline: 12 months
  Phase 1: Requirements & Design (3 months)
  Phase 2: Development & Integration (3 months)
  Phase 3: UAT & Deployment (3 months)
  Phase 4: Post-implementation & Training (3 months)
Cost:
Project Management & Coordination: Rs. 800,000
Implementation & Testing: Rs. 1,200,000

## Slide 18: Resources
Budget – Cost Allocation
Total Budget: Rs. 35,000,000
Breakdown:
Hardware (Servers, Network): Rs. 5,000,000
Software (ERP Licenses, Tools): Rs. 15,000,000
Training (Workshops, Documentation): Rs. 1,500,000
Consulting & Services: Rs. 7,500,000
Third-Party Software Evaluation: Rs. 500,000
Site Visits & Demos: Rs. 300,000
Dataquest Reports: Rs. 200,000
Total Estimated Project Cost: Rs. 35,500,000

## Slide 19: Risk
Resistance to Change
  Risk: User resistance due to familiarity with legacy system.
  Impact: Slow adoption, productivity dip.
ROI Justification
  Risk: Difficult to quantify benefits (ease of use, speed, support).
  Impact: Management struggles with buy-in.
Integration Issues
  Risk: Compatibility challenges with legacy systems.
  Impact: Delays, additional costs.
Training Overhead
  Risk: Extensive training for 500 users.
  Impact: High costs, productivity loss.

## Slide 20: Risk
5. Data Migration Risks
  Risk: Data loss or corruption during migration.
  Impact: Inaccurate data, delays.
6. Performance Gaps
  Risk: New system may underperform expectations.
  Impact: User dissatisfaction.
7. Support Complexity
  Risk: Increased maintenance challenges.
  Impact: Higher operational costs.
8. Overcomplicated Features
  Risk: Unnecessary or complex features.
  Impact: Underutilization.

## Slide 21: Risk
9. Budget Overruns
  Risk: Unexpected development or integration costs.
  Impact: Budget exceeds by Rs. 2M-3M.
10. Change Management Failure
  Risk: Poor adoption due to ineffective change management.
  Impact: Low user morale, failure to implement.