## Slide 1: CTS Support
Prepared By – Rohit Salvi
Date – 05.01.2025

## Slide 2: Situation
The Cheque Truncation System (CTS) is a technologically driven technique for processing physical paper cheques quicker with greater effectiveness. It is a technology that seeks to eliminate the need for paper cheques to be physically transported from one bank to another during the clearing process. It is commonly known as CTS. CTS stands for Cheque Truncation System (CTS).
CTS clearing is divided into 3 Grids, i.e. North, South and West Grid. At IDFC First Bank all branches do cheque collection for clients which is then handed over to third party vendor for processing (Cheque scanning activity).
All three Grids have central processing clearing team. Branched earlier used to complete cheque reporting via Email which consisted of excel format mentioning client account number, cheque number and cheque amount.

## Slide 3: Situation
For instance, West Grid has a total of approximately 330 branches and a daily cheque collection count of approximate 10,000.00 cheques.
It was observed by Central clearing processing team that daily monitoring of branches cheque reporting emails and collating of cheque lodgment data has become a tedious task.
To overcome these challenges CTS Support application was identified as a solution which would require all branches to update client account number, cheque number and cheque amount CTS Support application. Post which cheque lodgment data would be created in an excel format. This data from each individual branches can be accessed by Central clearing processing team.

## Slide 4: Situation
The process of email reporting is thus eradicated and Central clearing processing team can collate the data from CTS Reporting application itself.

## Slide 5: Goals
The purpose of this project is to mitigate the tedious task of daily mail monitoring and cheque lodgment data collation. This would help in faster processing of cheques and avoid any mis outs/ errors.
We have identified CTS Support application to enable cheque lodgment reporting via centralized application and eliminate email reporting.
This application would assist central clearing processing team in seamless processing of cheques and identify cheque differences if any, with more faster resolutions and timely cheque lodgments with NPCI cut-off.

## Slide 6: Project Objectives
Understand Client needs
Provide Best Service
Achieve highest client satisfaction levels
Adhere to banks laid down process and policies
Increase banks Client Base
Contribute towards banks profitability
Seamless cheque reporting
Streamline cheque lodgment process

## Slide 7: Project Objectives
Reduce the error rates
Implementation of CTS reporting application
Centralized tracker for cheque collection
Allocate the budget
Identify risks and challenges

## Slide 8: Project Objectives
Identify the resources
Build high performance team
Improve technical and analytical skills
Improve productivity with cross functional team
Create a performance focused culture

## Slide 9: Success Criteria
Meeting the user requirements
Cheque collection reporting to be done via CTS Support Application only
Minimal mail exchanges for cheque reporting's
Reduction in errors
Minimal time taken for identification of cheque lodgment differences, if any
Successful Implementation of CTS Support Application
Project to be completed within given timeframe
Project to be completed within budget

## Slide 10: Success Criteria
Project to completed with allocated resources
Successful updation of cheque collection data
Successful maintenance of cheque collection data at central level
Best optimal CTS Support application performance
Positive client feedback
Faster cheque processing
Successful cheque lodgment within NPCI Turn Around TAT

## Slide 11: Methods / Approach
Bank has appointed a Cheque Clearing Committee consisting of Clearing Head, Branch Control Unit Head, Internal Audit Head, Information Technology Head.
After evaluation of existing cheque reporting process, it is recommended for introduction of CTS Reporting application for all branches at bank level
CTS Reporting application to include the following features for reporting purpose
a. Branch Code - Mandatory
b. Cheque Category- Mandatory

## Slide 12: Methods / Approach
c. Client Account Number– Mandatory
d. Cheque number– Mandatory
e. Cheque Amount - Mandatory
Since CTS reporting would be a new application with bank. Request for Proposal (RFP) Request for Information (RFI) and Request for Quotation (RFQ) is asked for. After having Pre-Bid conference Statement of Work (SOW) would be finalized
Technical Team consisting of Project Manager, Business Analyst, Java Developers, Testers and Data Base Developers is identified for this project

## Slide 13: Methods / Approach
Technical Team consisting of Project Manager, Business Analyst, Java Developers, Testers and Data Base Developers is identified for this project
Bank has identified Project Head, SME and experienced end users for the project
Business Analyst has first identified the project goals and objectives
Business Analyst has done GAP and SWOT analysis
Business Analyst has then done the stakeholder analysis for this project using RACI Matrix

## Slide 14: Methods / Approach
Business Analyst has done requirement gathering from Bank end using elicitation techniques like document analysis, brainstorming, interviews and observations
Business Analyst has then documented the requirement in Business Requirement Document.
Business Analyst then proceeds to UML Diagrams ( Use Case and Activity Diagram) and also prepares Functional and Non Functional Requirement Documents, Software Requirements Specification and RTM
Business Analyst has then completed Knowledge Transfer to its Development team regarding the requirements

## Slide 15: Methods / Approach
Development Team works of development and Coding part
Testers to then test application functionality and identity and fix the bugs
UAT testing to be arranged by Business Analyst with trained bank end users
Post satisfactory confirmation from Banks Project Head, business analyst to get a sign – off
CTS Support Application to deployed for Live Environment
Application maintenance to implemented
Gather Bank feedback

## Slide 16: Resources
Bank Committee : Ms. Priyanka – Project Head
Mr. Rajesh – SME
Ms. Harshita & Ms. Devika – End User
Salesforce Team : Mr. Hanumant - Project Leader
Mr. Rohit – Business Analyst
Mr. Gajanan & Mr. Yogesh - Java Developers
Ms. Madhuri & Ms. Anshika – Testers
Ms. Sneha – Database Admin

## Slide 17: Resources
Time – 12 Months maximum time frame
Budget - Not exceeding 1 Crore
Project Size – Medium 500 to 1000 Man Hours
Software – JavaScript, HTML.
Hardware – Bank Server, Hard Disk.
Documents – Existing SOP and reporting format.

## Slide 18: Risks and Dependencies
Change Request
Budget Vs Expectations
Lack Of Collaboration
Rules and regulations
Stakeholders availability
Resource dependencies
User Expertise

## Slide 19: Executive Summary
Current State – Cheque lodgment reporting done via emails only
Email is the only source for communication
Tedious task for collating the data
Future State – Cheque lodgement reporting to be done via CTS Support
Application
Consolidated data available across the clearing Grids
Introduction of CTS Support Application will help the bank in faster processing of CTS cheques. Also the cheque lodgment data would be centrally available in the system for ready reference. Process of collating of cheque deposition data basis email would be eliminated. Effective tool for data storage.