**AGILE DOCUMENTS**

**Document 1: Definition of Done Checklist for a Fraud Management Project:**

|  |  |  |
| --- | --- | --- |
| **Checklist Item** | **Description** | **Status** |
| 1. Produced Code for Presumed Functionalities
 | All planned functionalities, as per user stories, have been implemented. | Pending/Done |
| 1. Assumptions of User Story Met
 | All business and technical assumptions in the user story are validated and fulfilled. | Pending/Done |
| 1. Project Builds Without Errors
 | The code compiles successfully with no errors in the build pipeline. | Pending/Done |
| 1. Unit Tests Written and Passing
 | Unit tests cover the agreed minimum coverage and pass successfully. | Pending/Done |
| 1. Project Developed on Test Environment
 | Development and testing performed on an environment identical to production. | Pending/Done |
| 1. Test on Devices/Browsers Listed Passed
 | Feature tested on all supported devices, browsers, and platforms as listed in project assumptions.  | Pending/Done |
| 1. Feature OK-ed by UX Designer
 | UX design and usability approved by the UX designer | Pending/Done |
| 1. QA Performed and Issues Resolved
 | QA validated the features, and all issues raised are resolved. | Pending/Done |
| 1. Feature Tested Against Acceptance Criteria
 | Feature satisfies all acceptance criteria and business requirements. | Pending/Done |
| 1. Feature OK-ed by Product Owner
 | The Product Owner has reviewed and approved the completed feature. | Pending/Done |
| 1. Refactoring Completed
 | Code refactoring is performed to enhance maintainability and performance. | Pending/Done |
| 1. Configuration or Build Changes Documented
 | Any system configuration or build changes are documented clearly. | Pending/Done |
| 1. Documentation Updated
 | User guides, technical specs, and other documentation are updated as necessary. | Pending/Done |
| 1. Peer Code Review Performed
 | Code reviewed by peers and approved for quality and standards. | Pending/Done |

**Document 2- Product Vision**

|  |
| --- |
| **Scrum Project****Name: Mastercard Developer Zone (Fraud Management)** |
| **Venue: Kalpana Chawala meeting room** |
| **Date: 13/12/2024** | **Start Time: 10 am** | **End Time: 12 pm** | **Duration: 2 hrs** |
| **Client: Marian Western** |
| **Stakeholder List:**1. Vijay Singh
2. Rami Lengadhare
3. Puja Sahay
4. Komal Pardeshi
5. Jayashree Gosavi
 |
| **Scrum Team** |
| **Scrum Master:** Jayesh Rajput |
| **Product Owner:** Kunal Datta |
| **Scrum Developer 1:** Sandeep Goyal |
| **Scrum Developer 2:** Rakhi Thakare |
| **Scrum Developer 3:** Neeta Singh |
| **Scrum Developer 4:** Amit Verma |
| **Scrum Developer 5:** Digvijay Khade |
| **Scrum Developer 6:** Nikhil Sharma |
| **Vision:** To create an intelligent, adaptive, and user-friendly fraud management solution that proactively detects and prevents fraudulent activities in real time, safeguarding businesses and customers while ensuring compliance with regulatory standards.

|  |  |  |  |
| --- | --- | --- | --- |
| **Target Group** | **Needs** | **Product**  | **Value** |
| **Market Segment Addressed****Industries:**Financial Services (Banks, Payment Processors, FinTechs )E-Commerce and RetailInsurance Providers**Market Type:**Enterprises handling large-scale transactions or sensitive customer data.Business operating in high-risk environments prone to fraudulent activities.**Target Users and Customers****Primary User (Operational Level):****Fraud Analysts:** Investigating suspicious activities.**Risk Management Teams:** Monitoring fraud trends and preventing losses.**Compliance Officers:** Ensuring adherence to regulations like AML, PCI-DSS, GDPR.**IT Teams:** Managing system integration and performance.**Customers (Decision-Makers):**C-Level ExecutivesRisk Managers and DirectorsBusiness OwnersGovernment and Regulatory Bodies | **Problem the Product Solves****1. Fraud Detection and Prevention:*** Identifies and mitigates fraudulent activities in real-time (e.g. transaction fraud, identity theft).
1. **Operational Inefficiency:**
* Reduces the time and resources spent on manual fraud detection processes.
1. **Financial Loss:**
* Minimize monetary losses caused by fraud across industries.

**Benefits Provided**1. **Enhanced Security:**
* Provides businesses with robust fraud prevention mechanism and data.
1. **Real-Time Insights:**
* Delivers actionable alerts and insights for swift decision-making.
 | The product is an **intelligent fraud management system** that combines advanced analytics, machine learning, and real-time monitoring to detect, prevent and mitigate fraudulent activities across industries.**What Makes it Desirable and Special?**1. **Real-Time Fraud Detection:**
* Uses AL/ML algoriths to identify suspicious patterns and anomalies as they occur.
1. **Comprehensive Coverage:**
* Monitors transactions, user behaviour, and other critical data points across multiple channels (web, mobile, APIs)

**Is it Feasible to Develop the Product?**Yes, the product is feasible to develop considering the following factors:1. **Technological Maturity:**
* Proven technologies like AI/ML, big data analytics, and cloud computing are available to support the system.
1. **Market Demand:**
* Growing need across industries for robust fraud management solutions.
 | **How the Product Benefits the Company**1. **Revenue Protection:**

Reduces finacial losses caused by fraud, ensuring profitability.1. **Market Differentiation:**

Positions the company as a trusted provider of fraud prevention solutions, enhancing its competitive edge.**Business Goals**1. **Increase Market Share:**

Capture a significant portion of the fraud prevention market across industries.1. **Revenue Growth:**

Achieve profitability through subscription-based or licensing revenue streams.1. **Strength Brand Reputation:**

Establish the company as a trusted leader in fraud management solutions. |
|  |  |  |  |

 |

**Document 3: User stories**

|  |  |  |
| --- | --- | --- |
| **User story No:** 1 | **Tasks:** 1. Define criteria for suspicious activities.
2. Implement real-time monitoring system.
3. Test with historical data
 | **Priority:**High |
| **Value Statement:**As a user, I want to detect suspicious transactions in real-time, so that I can minimize potential losses. |
| **BV:** Prevent financial loss | **CP:** Increase user trust |
| **Acceptance criteria:-** Transactions flagged for anomalies within 5 seconds.* Alert sent to the appropriate team.
 |

|  |  |  |
| --- | --- | --- |
| **User story No: 2** | **Tasks: 1.** Design report templates.2. Integrate with data base.3. Ensure real time updates. | **Priority:** Medium |
| **Value Statement:** As user, I want to view detailed reports of fraudulent activities, so that I can analyze patterns |
| **BV:** Identify recurring fraud trends | **CP:** Support strategic decisions. |
| **Acceptance criteria:** - Reports generated in under 2 minutes.* Includes key details like time, amount, and pattern description.
 |

|  |  |  |
| --- | --- | --- |
| **User story No: 3** | **Tasks:** 1. Establish account blocking criteria.2. Automate the blocking process.3. Notify users of actions taken. | **Priority:** High |
| **Value Statement:** As a user, I want to block the flagged accounts automatically, so that I can prevent further fraud. |
| **BV:** Protect system integrity. | **CP:** Reduce manual effort. |
| **Acceptance criteria:*** Accounts flagged as fraudulent are blocked instantly.
* Notifications sent within 5 minutes.
 |

|  |  |  |
| --- | --- | --- |
| **User story No: 4** | **Tasks:** 1. Develop a review dashboard.2. Implement an approval workflow.3. Log reviewer actions.  | **Priority:** Medium |
| **Value Statement:** As a user, I want to review flagged transactions manually, so that I can verify false positives. |
| **BV:** Improve fraud detection accuracy. | **CP:** Minimize customer inconvenience. |
| **Acceptance criteria:**- Reviewers can access transactions easily.* Decisions logged with time stamps.
 |

|  |  |  |
| --- | --- | --- |
| **User story No: 5** | **Tasks:** 1. Define risk thresholds.2. Create notifications on the system (email/SMS).3. Test notifications for speed. | **Priority:** High |
| **Value Statement:** As a user, I want to receive alerts for high-risk transactions, so that I can act immediately. |
| **BV:** Ensure quick responses to threats. | **CP:** Enhance system responsiveness. |
| **Acceptance criteria:** * Alerts received within 1 minute of detection.
* Include transaction details for quick actions.
 |

|  |  |  |
| --- | --- | --- |
| **User story No: 6.** | **Tasks:** 1. Develop a whitelist feature.2. Test with sample data.3. Allow updates to the whitelist | **Priority:** Low |
| **Value Statement:** As a user, I want to whitelist trusted user, so I can reduce false positive. |
| **BV:** Optimize fraud detection | **CP:** Improve user experience. |
| **Acceptance criteria:*** Trusted users bypass fraud checks successfully.
* Whitelist updated without errors.
 |
|  |

**Document 4: Agile PO Experience**

The Product Owner plays a critical role in defining and delivering a fraud management product by blending domain expertise with market awareness. Below are the responsibilities tailored to a fraud management project:

1. Market Analysis:
* The PO conducts thorough research on **market needs and demand** for fraud detection and prevention solutions.
* The PO analyzes trends in **fraudulent activities** across industries (e.g. financial services, e-commerce, insurance).
* Study **competitive products** in the fraud management domain to identify unique selling points (USPs) and gaps.
* Assess emerging technologies like AI, machine learning, and behavioral analytics for fraud detection.
* Engage with industry experts, regulatory bodies, and stakeholders to understand **compliance requirements.**
1. **Enterprise Analysis:**

In a fraud management project, Enterprise Analysis focuses on evaluating the feasibility, value, and alignment of the product with organizational goals.

* **Due Diligence on Market Opportunities:**

The PO assesses the financial and strategic opportunity of developing a fraud management system. This involves understanding the customer base (e.g. banks, fintech, e-commerce) and determining ROI based on the reduction in fraud incidents and compliance adherence.

1. **Product Vision and Roadmap**
* **Product Vision Keeping Market Analysis in Mind:**

The vision for the fraud management system is to create a robust, AI-driven, and adaptive tool that detects and prevents fraudulent activities in real time, ensuring minimal disruption to genuine users.

* **Product Roadmap with High-Level Features and Timelines:**

The roadmap includes milestones such as integrating machine learning models, multi-channel fraud detection, and providing advanced reporting tools. Timelines account for iterative development and continuous feedback.

1. **Managing Product Features**
* **Managing Stakeholder Expectations:**

The PO works closely with stakeholders like banks, security teams, and regulatory bodies to gather requirements and address their concerns.

* **Prioritization of Epics, Stories, and Features:**

Features such as real-time anomaly detection, user behavior analysis, and customizable risk scoring are prioritized based on criticality and ROI.

1. **Managing Product Backlog:**
* **Prioritization of User Stories:**

User stories like “As a fraud analyst, I want to receive real-time alerts for suspicious activities” are ranked based on urgency and user impact.

* **Re-Prioritization Based on Stakeholder Needs:**

Adjustments are made to address emerging threats or regulatory changes. For instance, a new law requiring detailed audit trails might lead to a reprioritization of backlog items.

1. **Managing Overall Iteration Progress**
* **Sprint Progress Review:**

The PO participates in sprint reviews to assess completed work, ensuring alignment with the product vision.

* **Re-Prioritization of Sprints and Epics if Needed:**

If market demands shift, such as an uptick in fraud via mobile channels, the PO adapts the roadmap to prioritize mobile-specific features.

* **Sprint Retrospectives with Business Analyst:**

Post-sprint reviews involve discussing challenges, such as delayed feedback from fraud analysts, and finding solutions to improve future iterations.

* **From this project I have learned how to handle sprint meetings such as**
1. **Sprint Planning Meeting:**
* Collaborated with the scrum Master and Development Team to define sprint aligned with the product roadmap.
* Prioritized user stories from the product backlog based on their value and urgency, ensuring alignment with stakeholder needs.
* Clearly communicated acceptance criteria for features such as real-time fraud detection and customizable dashboards.
* Addressed any technical or functional queries from the team, ensuring the scope of work was well understood.
1. **Daily Scrum Meeting:**
* Participated as an observer to understand team progress and any roadblocks they faced, ensuring I could provide support where necessary.
* Provided clarifications on user stories to keep the team aligned with the sprint goal.
* Monitored progress on high-priority tasks like fraud alert system integration to ensure timely delivery.
1. **Sprint Review Meeting:**
* Reviewed the completed work with stakeholders, ensuring it met acceptance criteria and aligned with the fraud management vision.
* Demonstrated key features, such as machine learning-driven fraud detection, to stakeholders for feedback and validation.
* Documented feedback for refining or reprioritizing upcoming backlog items based on stockholder insights.
1. **Sprint Retrospective Meeting**
* Collaborated with the Scrum Master and team to reflect on what went well and areas for improvement.
* Discussed challenges like delays in third-party API integration for fraud detection and proposed solutions for early dependency management.
* Suggested process improvements, such as more frequent stakeholder check-ins to enhance communication and reduce rework.
1. **Backlog Refinement Meeting:**
* Engaged with the Business Analyst and team to refine and elaborate user stories, ensuring they were ready for upcoming sprints.
* Adjusted priorities based on emerging fraud trends or regulatory changes, such as the need for real-time compliance reporting.
* Also, User stories creation and what things will be included in user stories such as

**User Story Template**

1. **Story No:** Unique identifier for tracking (e.g. FMS-001)
2. **Title:** A short, descriptive title for the story.
3. **Description:** Follows the format:
* **As a** [type of user],
* **I want to [**perform an action**],**
* **So that [**achieve a goal**]**
1. **Tasks:** Key tasks needed to complete the story.
2. **Priority:** The level of importance (High, Medium, Low)
3. **Acceptance Criteria:** Clear conditions that must be met for the story to be considered done.
4. **BV (Business Value):** The value this story delivers to the business.
5. **CP (Complexity Points):** The estimated effort or complexity of the story.

 Example:

1. **Story No:** FMS-001
2. **Title:** Detect fraudulent transactions in real-time
3. **Description:**
* As a fraud analyst,
* I want the system to identify and flag suspicious transactions in real-time,
* So that I can review and take necessary action promptly.
1. **Tasks:**
* Integrate a rule-based fraud detection engine.
* Configure real-time transaction monitoring.
* Send flagged transactions to the review queue.
1. **Priority:** High
2. **Acceptance Criteria:**
* Transactions exceeding the predefined thresholds are flagged automatically.
* Notifications are sent to fraud analysts within 5 seconds of detection.
* A log of flagged transactions is maintained for further review.
1. **BV:** 8
2. **CP:** 5

**Document 5: Product and sprint backlog and product and sprint burndown Charts**

**Product backlog:**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **User Story ID** | **User Story** | **Tasks** | **Priority** | **BV** | **CP** | **Sprint** |
| US 001 | As a fraud analyst, I want to monitor transactions in real-time, so I can detect an opalise quickly. | Design a real-time monitoring dashboard and implement anomaly detection logic Integrate data streams for transactions. | High | 10 | 8 | Sprint 1 |
| US 002 | As a compliance, I want a report of flagged transactions, so I can meet regulatory requirements. | Define reporting templates, implement data export functionality, and add filters for flagged transactions | High | 9 | 6 | Sprint 1 |
| US 003 | As a risk manager, I want AI-powered risk scoring, so I can prioritize potential threats. | Develop risk scoring model Train and test AI algorithms Integrate scoring into dashboards. | High | 10 | 10 | Sprint 2 |
| US 004 | As a fraud analyst, I want to customize detection rules, so I can adapt to changing fraud patterns. | Create rule editor UI-Implement rule engine backend Test rule application on sample data. | Medium | 8 | 7 | Sprint 2 |
| US 005  | As an IT admin, I want to configure access controls, so only authorized user can access the system. | Design role-based access control system- Develop user authentication mechanism. Test permission | Medium | 7 | 5 | Sprint 3 |
| US 006 | As a business owner, I want a summary dashboard,, so I can track overall fraud trends at a glance. | Design dashboard layout.* Implement trend analysis charts- Test summary report generation.
 | Low | 6 | 4 | Sprint 3 |



**Sprint backlog:**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **User Story ID** | **User Story** | **Tasks** | **Owner** | **Status** | **Estimated efforts** |
| US 001 | As a fraud analyst, I want to monitor transactions in real-time, so I can detect anomalies quickly. | Design a real-time monitoring dashboard to implement anomaly detection logic and integrate data streams for transactions. | Developer A | In-progress | 16 |
| US 002 | As a compliance officer, I want a report of flagged transactions, so I can meet regulatory requirements. | Define reporting templates and implement Data export functionality. | Developer B | Not started | 12 |
| US 003 | As a risk manager, I want AI-powered risk scoring, so I can prioritize potential threats. | Develop risk scoring model Train and test AI algorithms Integrate scoring into the dashboard | Data Scientist C | In progress | **20** |
| US 004  | As a fraud analyst, I want to customize detection rules, so I can adapt to changing fraud patterns. | * Create rule edit or UI-Implement rule engine backend-Test rule application on sample data.
 | Developer (Amit Verma) | Not Started | 15 |
| US 005 | As an IT admin, I want to configure access controls, so that only authorized users can access the system | * Design a role-based access control system Develop a user authentication mechanism.
* Test permission
 | Developer (Kunal Datta) | Not Started | **10** |



**Document 6: Sprint meetings**

**Meeting TypeMeeting Type 1: Sprint Planning meeting**

|  |  |
| --- | --- |
| **Date** | 1-12-2024 |
| **Time** | 10 am |
| **Location** | Pune |
| **Prepared By** | Komal Pardeshi |
| **Attendees**  | Rami Lengadhare, Puja Sahay, Nikhil Sharama, Digvijay Khade |

**Agenda Topics**

|  |  |  |
| --- | --- | --- |
| Topic | Presenter | Time allotted  |
| Introduction to Fraud Management | Rami Lengadhare | 10 |
| Types of Fraud | Sreelekha Ashok | 15 |
| Fraud Detection Technique | Puja Sahay | 15 |
| Case studies | Nikhil Sharma | 20 |
| Fraud Prevention Strategies | Digvijay Khade | 25 |
| Tools and Technologies in Fraud | Amruta Patil | 15 |
| Q & A Session | Sujoy Datta | 20 |

**Other Information:**

|  |  |
| --- | --- |
| **Category** | **Details**  |
| **Observers** | Aarju Patel |
| Ketan Somane  |
| Pratik Sawant |
| **Resources** | **Presentation Slides** |
| * Fraud Management Software (Azure)
 |
| * Internet Access
 |
| * Reference Documents (case studies)
 |
| **Special Notes** | * Ensure all participants have access to the necessary resources beforehand.
 |
| * Q & A session to be moderated by Pallavi Patil
 |
| * Observer to provide feedback at the end of the session.
 |
| * Backup of all materials to be stored on TRC for future use.
 |

**Meeting Type 2:** **Sprint review meeting**

|  |  |
| --- | --- |
| **Date** | 13-12-2024 |
| **Time**  | 12 pm |
| **Location** | Homi Bhabha meeting room  |
| **Prepared By** | Komal Pardeshi |

|  |  |  |  |
| --- | --- | --- | --- |
| **Sprint status** | **Things to demo** | **Quick updates** | **What’s next** |
| Current Sprint: Sprint 3 | Fraud detection workflow (UI/UX) | * The fraud prevention module is in final testing phase
 | Begin integration testing with payment gateway systems |
| Overall Status: On Track/At Track/ Delayed | * Reports generated from fraud detection module
 | * Stakeholder review schedule for Date
 | * Conduct a workshop for end users on fraud alert dashboards
 |
| Key Completed Tasks:- Finalized fraud detection requirements- Integrated fraud detection algorithm- Prepared user stories for fraud prevention workflows Pending Tasks:- Test validation for fraud alerts- Stakeholder review of the case study moduleBlockers:* Delayed feedback from Nikhil Mane- Dependency on third-party fraud detection API integration
 | * Sample fraud case study documentation
 | * QA team identified and fixed [3] of bugs
 | * Complete documentation for fraud detection guidelines.
 |

**Meeting Type 3: Sprint retrospective meeting**

|  |  |
| --- | --- |
| Date | 23-12-2024 |
| Time | 10 am |
| Location | Rameswaram meeting room |
| Prepared By | Komal Pardeshi |
| Attendees | Rami Patil |
|  | Manoj Kumar |
|  | Jaykirthee Nayar |
|  | Poonam Wagh |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Agenda** | **What Went Well** | **What Didn’t Go Well** | **Questions** | **References** |
| 1. Welcome and Objectives of the Retrospective
 | * Fraud detection requirements were finalized ahead of schedule.
 | * Delays in third-party API responses affecting integration timelines.
 | * What steps can we take to avoid rework in the next sprint?
 | * Sprint Goal Document (3)
 |
| 1. Review of Sprint Goals
 | * Seamless collaboration between the development and QA teams
 | * Limited testing resources led to a backlog in test cases.
 | -How can we communicate between stakeholders and the team? | * Project Timeline and Deliverable Plan
 |
| 1. Discuss “What Went Well”
 | * Successful integration of fraud detection tools with the existing system.
 | * Miscommunication on fraud alert dashboard requirements causes rework.
 | * What additional resources or tools do we need to address current blockers?
 | * Issue/Bug Tracker Logs
 |
| 1. Discuss “What didn't Well”
 | Delay in third-party API responses affecting integration timelines | * Insufficient time allocated for stakeholder's training.
 | * Are there any process improvements to speed up API integration?
 | * Stakeholder Feedback from Sprint Demo
 |
| 1. Identify Improvement Areas
 | Finalized fraud detection requirements ahead of schedule. | Misalignment in understanding fraud alert dashboard requirements caused rework  | What measures can be taken to prevent rework in requirements? | Stakeholder Feedback Notes from Sprint Demo |
| 1. Action Items and Next Steps
 | The team met 90% of the sprint goals on time, despite external challenges. | Limited test coverage for edge cases due to insufficient time and resources. | What strategies can be implemented to improve test coverage for edge cases? | Test Coverage Metrics Report |
| 1. Wrap-Up and Closing Remarks
 | Resolved critical issues in the fraud reporting module ahead of the deadline. | Limited focus on user training and onboarding processes. | How can we improve our testing strategy to cover all edge cases in the next sprint? | Test Reports Highlighting Gaps and Coverage |

**Meeting Type 4: Daily Stand-up meeting**

|  |  |  |  |
| --- | --- | --- | --- |
| **Question** | **Name/Role** |  | **Week “X” (from dd-mm-yyyy to dd-mm-yyyy)** |
| Monday | Tuesday | Wednesday | Thursday |  | Friday | Saturday | Sunday |  |
| **What did****you do****yesterday?** | * Amruta Madale
* Sumit Solankar
* Nikhil Sharma
 | * Designed the real-time monitoring dashboard.
* Started integrating transaction data streams.
 | * Finished integrating data streams.
* Developed initial anomaly detection algorithm.
 | -Tested anomaly detection logic.- Made adjustments based on the test results.- Refined dashboard layout. |  |  |  |  |  |  |
| **What will****you do****today?** | * Puja Patil
* Sarika Raghuvanshi
* Raj Pardeshi
 | * Complete data stream integration.
* Begin implementing anomaly detection logic.
 | * Test anomaly detection logic.
* Refine monitoring dashboard layout.
 | Implement filters for flagged transactions in compliance reports. |  |  |  |  |  |  |
| **What (if****any) is****blocking****your****progress?** | * Sachin Raghuvanshi
* Sahil Kamble
* Aarju Patel
 | None | Delay in receiving test data from QA team. | Dependency on database configuration updates |  |  |  |  |  |  |

|  |  |  |
| --- | --- | --- |
| **Question** | Thursday | Friday |
| **What did****you do****yesterday?** | * Implemented filters for flagged transactions.
* Completed export functionality for compliance reports.
 | * Completed rule editor UI draft.
* Finalized user authentication design.
 |
| **What will****you do****today?** | * Start working on rule editor UI.
* Draft user authentication mechanism design.
 | * Conduct peer reviews of implemented features.
* Resolve pending bugs.
 |
| **What (if****any) is****blocking****your****progress?** | * Pending confirmation rule editor specs.
 | None  |